## Product
Defect # | Status | Raised By | Tested on Version | Test Case ID | Expected Result | Actual Result | Priority | Severity
1 | Open | Toni Ihab | V1 | PP02 | Search results match the keyword and filters. | Search results cannot match the keyword and filters at the same time | Medium | Medium
2 | Open | Toni Ihab | V1 | PP03 | "No results found" message is displayed. | No error flash message, No products displayed though | Medium | Medium
3 | Open | Toni Ihab | V1 | PP04 | "Invalid search term" OR no results. | No "Invalid search term", No results displayed though | Medium | Medium
4 | Open | Toni Ihab | V1 | PP11 | Products from both categories are displayed. | Cannot select more than one category together | Medium | Medium
5 | Open | Toni Ihab | V1 | PP12 | "No products found" message is displayed. | No empty Category exists, Cannot confirm | Medium | Medium
6 | Open | Toni Ihab | V1 | PP13 | All products are displayed regardless of category. | No reset filters button found | Medium | Medium
7 | Open | Toni Ihab | V1 | PP15 | Products from both brands are displayed. | Cannot select more than one category together | Medium | Medium
8 | Open | Toni Ihab | V1 | PP17 | All products are displayed. | No reset filters button found | Medium | Medium
9 | Open | Toni Ihab | V1 | PP18 | "No products found" message is displayed. | No empty Category exists, Cannot confirm | Medium | Medium
10 | Open | Toni Ihab | V1 | PP27 | Error message: "This product is out of stock." | No product out of stock exists, Cannot confirm | Medium | Medium
11 | Open | Toni Ihab | V1 | PP28 | Error message: "Maximum 5 units allowed."<br>Cart quantity defaults to 5 | There is no realistic stock limit | High | High
12 | Open | Toni Ihab | V1 | PP30 | Cart is not updated<br>Login/registration page loads | Cart retains the item. | High | High
13 | Open | Toni Ihab | V1 | PP31 | System displays error: "Numbers are not allowed" | Field saved | Medium | Medium
14 | Open | Toni Ihab | V1 | PP32 | System displays error: "Special characters are not allowed" | Field saved | Medium | Medium
15 | Open | Toni Ihab | V1 | PP33 | System displays error: "Field is required" | Field saved | Medium | Medium
16 | Open | Toni Ihab | V1 | PP34 | System displays error: "First character cannot be space" | Field saved | Medium | Medium
17 | Open | Toni Ihab | V1 | PP36 | System displays error: "Exceeds character limit" | Field saved | Medium | Medium
18 | Open | Toni Ihab | V1 | PP37 | System displays error: "Field is required" | Field saved | Medium | Medium
19 | Open | Toni Ihab | V1 | PP38 | System displays error: "First character cannot be space" | Field saved | Medium | Medium
20 | Open | Toni Ihab | V1 | PP39 | System displays error: "Spaces are not allowed" | Field saved | Medium | Medium
21 | Open | Toni Ihab | V1 | PP40 | System displays error: "Invalid input" | Field saved | Medium | Medium
22 | Open | Toni Ihab | V1 | PP41 | System displays error: "Invalid input" | Field saved | Medium | Medium
23 | Open | Toni Ihab | V1 | PP42 | System displays error: "Invalid input" | Field saved | Medium | Medium
24 | Open | Toni Ihab | V1 | PP43 | System displays error: "Invalid input" | Field saved | Medium | Medium
25 | Open | Toni Ihab | V1 | PP45 | System displays error: "Invalid input" | Field saved | Medium | Medium
26 | Open | Toni Ihab | V1 | PP46 | System displays error: "Invalid input" | Field saved | Medium | Medium
27 | Open | Toni Ihab | V1 | PP47 | System displays error: "Invalid input" | Field saved | Medium | Medium
28 | Open | Toni Ihab | V1 | PP48 | System displays error: "Invalid input" | Field saved | Medium | Medium
29 | Open | Toni Ihab | V1 | PP49 | System displays error: "Invalid input" | Field saved | Medium | Medium
30 | Open | Toni Ihab | V1 | PP50 | System displays error: "Invalid input" | Field saved | Medium | Medium
31 | Open | Toni Ihab | V1 | PP51 | System displays error: "Invalid input" | Field saved | Medium | Medium
32 | Open | Toni Ihab | V1 | PP53 | Product is visible to users<br>API returns OK | Cannot be tested at the moment | Medium | Medium
33 | Open | Toni Ihab | V1 | PP54 | Error Message: Fill out all required fields | Cannot be tested at the moment | Medium | Medium
34 | Open | Toni Ihab | V1 | PP55 | Error message: "Product not found" | Cannot be tested at the moment | Medium | Medium
35 | Open | Toni Ihab | V1 | PP56 | Price updates globally | Cannot be tested at the moment | Medium | Medium
36 | Open | Toni Ihab | V1 | PP57 | Product is removed from listings | Cannot be tested at the moment | Medium | Medium

## Sign Up
Defect # | Status | Raised By | Tested on Version | Test Case ID | Expected Result | Actual Result | Priority | Severity
1 | Open | Abdo Mohamed | V1 | SU01 | System not accept Name Field | System Accept Name Field | Medium | Medium
2 | Open | Abdo Mohamed | V1 | SU02 | System not accept password | System Accept Weak Password | Medium | Medium
3 | Open | Abdo Mohamed | V1 | SU03 | System no accept first name | System Accept "First Name" Field | Medium | Medium
4 | Open | Abdo Mohamed | V1 | SU04 | System no accept last name | System Accept "Last Name" Field | Medium | Medium
5 | Open | Abdo Mohamed | V1 | SU05 | System not Accept Company | System accept Company | Medium | Medium
6 | Open | Abdo Mohamed | V1 | SU06 | System no Accept Company | System accept Company | Medium | Medium
7 | Open | Abdo Mohamed | V1 | SU07 | System no Accept Address2 | System accept Address2 | Medium | Medium
8 | Open | Abdo Mohamed | V1 | SU08 | System not accept Address2 field | System accept Address2 | Medium | Medium
9 | Open | Abdo Mohamed | V1 | SU09 | System no Accept Country | System Accept Country | Medium | Medium
10 | Open | Abdo Mohamed | V1 | SU10 | Only one radio button should be selected at any time | Dopdowns are be multible selected and have more input | Low | Low

## Contact Us
Defect # | Status | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
1 | open | ammar ashraf | V1 | CU02 | 1-go to contact us page 2- leave name field empty 3- Click Submit | System displays error message indicating "Name is required" | the form accepts the empty field | Medium | Medium
2 | open | ammar ashraf | V2 | CU03 | 1-Enter numbers in the Name field 2-Click Submit | System displays error message indicating "Name should be letters only" | the form accepts the numbers | Medium | Medium
3 | open | ammar ashraf | V3 | CU04 | 1-Enter special characters in the Name field 2-Click Submit | System displays error message indicating "Name should be letters only" | the form accepts the special characters | Medium | Medium
4 | open | ammar ashraf | V4 | CU10 | 1-go to contact us page 2- leave subject field empty 3- Click Submit | System displays error message indicating "subject is required" | the form accepts the subject empty field | Medium | Medium
5 | open | ammar ashraf | V5 | CU12 | 1-go to contact us page 2- leave message field empty 3- Click Submit | System displays error message indicating "message is required" | the form accepts the message empty field | Medium | Medium
6 | open | ammar ashraf | V6 | CU16 | 1- Click on Choose File 2- Click Submit | System displays error message indicating "please upload file with valid format" | System accepts the form | Low | Low
7 | open | ammar ashraf | V7 | CP12 | 1- go to https://www.automationexercise.com/products 2- add negative product quantity to cart 3- go to https://www.automationexercise.com/products | System displays error message indicating "quantity should be positive only" | the system accepts negative quantity | High | Low
8 | open | ammar ashraf | V8 | CP13 | 1- go to https://www.automationexercise.com/products 2- add negative product quantity to cart 3- go to https://www.automationexercise.com/products | System displays error message indicating "quantity should not be zero" | the system accepts zero quantity | Low | Medium
9 | open | ammar ashraf | V9 | CP16 | 1- go to https://www.automationexercise.com/view_cart 2- click on product description | redirect user to product page | user redirected to cart page | Low | Low
10 | open | ammar ashraf | V10 | CP29 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter numbers in name field empty 4-click pay and confrim order | System displays error message indicating "Name should be letters only" | the system accepts the numbers | Medium | Medium
11 | open | ammar ashraf | V11 | CP30 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter special characters in name field empty 4-click pay and confrim order | System displays error message indicating "Name should be letters only" | the system accepts the special characters | Medium | Medium
12 | open | ammar ashraf | V12 | CP33 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter letters and special characters card number field empty 4-click pay and confrim order | System displays error message indicating "card number must be numbers only" | The system accepts card number Field | Medium | Medium
13 | open | ammar ashraf | V13 | CP41 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 11 numbers card number field empty 4-click pay and confrim order | System displays error message indicating "card number invalid" | System accepts card number Field | Medium | Medium
14 | open | ammar ashraf | V14 | CP42 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 17 numbers card number field empty 4-click pay and confrim order | System displays error message indicating "card number invalid" | System accepts card number Field | Medium | Medium
15 | open | ammar ashraf | V15 | CP43 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 18 numbers card number field empty 4-click pay and confrim order | System displays error message indicating "card number invalid" | System accepts card number Field | Medium | Medium
16 | open | ammar ashraf | V16 | CP44 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 20 numbers card number field empty 4-click pay and confrim order | System displays error message indicating "card number invalid" | System accepts card number Field | Medium | Medium
17 | open | ammar ashraf | V17 | CP46 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter letters and special characters CVC field 4-click pay and confrim order | System displays error message indicating "CVC must be numbers only" | The system accepts CVC Field | Medium | Medium
18 | open | ammar ashraf | V18 | CP47 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter two digits in CVC field empty 4-click pay and confrim order | System displays error message indicating "CVC must be 3 or 4 numbers" | The system accepts CVC Field | Medium | Medium
19 | open | ammar ashraf | V19 | CP48 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter five digits CVC field empty 4-click pay and confrim order | System displays error message indicating "CVC must be 3 or 4 numbers" | The system accepts CVC Field | Medium | Medium
20 | open | ammar ashraf | V20 | CP52 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter letters and special characters in month field 4-click pay and confrim order | System displays error message indicating "month must be numbers only" | system accepts month field | Medium | Medium
21 | open | ammar ashraf | V21 | CP53 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter letters and special characters in year field 4-click pay and confrim order | System displays error message indicating "year must be numbers only" | system accepts year field | Medium | Medium
22 | open | ammar ashraf | V22 | CP54 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 1 digit in month field 4-click pay and confrim order | System displays error message indicating "month must be 2 numbers " | system accepts month field | Medium | Medium
23 | open | ammar ashraf | V23 | CP55 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 3 digit in month field 4-click pay and confrim order | System displays error message indicating "month must be 2 numbers only " | system accepts month field | Medium | Medium
24 | open | ammar ashraf | V24 | CP57 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 3 digit in year field 4-click pay and confrim order | System displays error message indicating "year must be 4 numbers only " | system accepts year field | Medium | Medium
25 | open | ammar ashraf | V25 | CP58 | 1- go to https://www.automationexercise.com/checkout 2- click on place order 3-enter 5 digit in year field 4-click pay and confrim order | System displays error message indicating "year must be 4 numbers only " | system accepts year field | Medium | Medium